## Project
Project_Status | Yet to Start
About_the_Project
Name | Android Tab App for those who don't use Windows
Start Date | 2018-03-05
End Date | 2018-04-30

## Right Design Team
Name | Role | Email | Phone | Available | Not_Available | Anything_Else
| Design Lead |  |  | Anytime
S UX
S UI
UX Writer
Mid
Other Skill
MiMi | Partner Relations | mimi@1thing.io
Danish Usmani | Head of Product | danish@1thing.io
Varun Gandhi | CEO | varun@1thing.io
Design Journeys | cc on emails | journeys@1thing.io

## Resources
Name | Purpose | Links
Workspace by 1THING | Collaboration | Link
Google Drive | Documents & Deliverables | Link
Invision | UX Prototype | Link
Invision | UI Prototype | Link
Invision | Assets | Link
Frontend | HTML/CSS/JS | Link

## Things To Do
Things_To_Do | Stages | Ownership | Hours(Min) | Hours(Max) | Timeline | Stage_Status
Create a Project Plan | Planning | DL | 10 | 12 | 2018-03-12 | Yet to Start
Initial Discussions | Sprint | DL |  |  |  | Yet to Start
Doc: Product & Users
Strategy Doc: UX/UI
Feature 1 | Sketch | S UX |  |  |  | Yet to Start
Information Architecture | UX + UI | S UX |  |  |  | Yet to Start
Visual Moodboard |  | S UI
Feature 1 |  | S UX + S UI
Feature 2 |  | Mid
Feature 3 |  | Mid
Assets & Guides | Handoff | Mid |  |  |  | Yet to Start
Working with developers | Support | Mid |  |  |  | Yet to Start
|  |  | 10 | 12

## Daily Updates
Dates | Things_To_Do | Stages | Add_a_State | Add_a_Tag | Add_another_Tag | Overall_Status | Deliverable_Link | Comments(if_any) | Hours_Spent | Hours:DL | Hours:S.UX | Hours:S.UI | Hours:Mid
2018-03-05 | [8 empty] | 0
2018-03-06 | [8 empty] | 0
2018-03-07 | [8 empty] | 0
2018-03-08 | [8 empty] | 0
2018-03-09 | [8 empty] | 0
2018-03-10 | [8 empty] | 0
2018-03-11 | [8 empty] | 0
2018-03-12 | [8 empty] | 0
2018-03-13 | [8 empty] | 0
2018-03-14 | [8 empty] | 0
2018-03-15 | [8 empty] | 0
2018-03-16 | [8 empty] | 0
2018-03-17 | [8 empty] | 0
2018-03-18 | [8 empty] | 0
2018-03-19 | [8 empty] | 0
2018-03-20 | [8 empty] | 0
2018-03-21 | [8 empty] | 0
2018-03-22 | [8 empty] | 0
2018-03-23 | [8 empty] | 0
2018-03-24 | [8 empty] | 0
2018-03-25 | [8 empty] | 0
2018-03-26 | [8 empty] | 0
2018-03-27 | [8 empty] | 0
2018-03-28 | [8 empty] | 0
2018-03-29 | [8 empty] | 0
2018-03-30 | [8 empty] | 0
2018-03-31 | [8 empty] | 0
2018-04-01 | [8 empty] | 0
2018-04-02 | [8 empty] | 0
2018-04-03 | [8 empty] | 0
2018-04-04 | [8 empty] | 0
2018-04-05 | [8 empty] | 0
2018-04-06 | [8 empty] | 0
2018-04-07 | [8 empty] | 0
2018-04-08 | [8 empty] | 0
2018-04-09 | [8 empty] | 0
2018-04-10 | [8 empty] | 0
2018-04-11 | [8 empty] | 0
2018-04-12 | [8 empty] | 0
2018-04-13 | [8 empty] | 0
2018-04-14 | [8 empty] | 0
2018-04-15 | [8 empty] | 0
2018-04-16 | [8 empty] | 0
2018-04-17 | [8 empty] | 0
2018-04-18 | [8 empty] | 0
2018-04-19 | [8 empty] | 0
2018-04-20 | [8 empty] | 0
2018-04-21 | [8 empty] | 0
2018-04-22 | [8 empty] | 0
2018-04-23 | [8 empty] | 0
2018-04-24 | [8 empty] | 0
2018-04-25 | [8 empty] | 0
2018-04-26 | [8 empty] | 0
2018-04-27 | [8 empty] | 0
2018-04-28 | [8 empty] | 0
2018-04-29 | [8 empty] | 0
2018-04-30 | [8 empty] | 0